## Slide 1: CNX308 Blount County Mandatory Pre-bid Meeting
August 4, 2023

## Slide 2: Alcoa Highway Corridor Improvements

## Slide 3: Stage 1 – PIN 101651.04 (CNX308)

## Slide 4: PIN 101651.02, .03, .04 and .05
ROW purchased under .02 and .03 PIN’s
Utilities coordinated under .02 and .03 and then re-evaluated under .04 and .05
Water quality permits (Individual ARAP and Individual 404) contain impacts for both .04 and .05 projects.
  As such, there will be more work included in the project permits than will be performed in the first stage of construction (101651.04).
  Additionally, these permits must remain open until all permitted work on both projects is complete.

## Slide 5: Key Stakeholders
McGhee Tyson Airport
Amazon
ARCONIC
Northpark Industrial Park
North-park
I-140
SR-115
SR-115
SR-162

## Slide 6: Design Features
Roadway Length – 1.687 Miles
Bridge Length – 0.694 Miles
6 Bridges
6 Retaining walls
2 Interchanges
  Including 1 system interchange
1 roundabouts
1 traffic signals
Continuation of the Blount County Greenway System
Natural Stream Installation
Expansion of ITS system
Lighting
https://youtu.be/yVB-ZuL7u3E

## Slide 7: Natural Stream Design
All excavation from the Natural Stream relocation sites have been determined to be suitable and has been included in the road and drainage excavation calculations

## Slide 8: Natural Stream Design – Inspector Requirements & Qualifications
CONSTRUCT NATURAL STREAM CHANNELS PURSUANT TO ALL PROVISIONS AND REQUIREMENTS OF APPLICABLE ARAPS, 404 PERMITS, NPDES PERMITS, AND PLANS
HAVE PRESENT ON-SITE, A NATURAL STREAM CHANNEL CONSTRUCTION/DESIGN EXPERT FOR ALL STREAM CHANNEL CONSTRUCTION ACTIVITIES TO ENSURE COMPLIANCE WITH THE PLANS AND PERMITS. THE NATURAL STREAM CHANNEL CONSTRUCTION/DESIGN EXPERT ON-SITE SHALL HAVE EXPERTISE IN NATURAL STREAM CHANNEL CONSTRUCTION, DESIGN, AND HAVE AT MINIMUM ONE OF THE FOLLOWING THREE QUALIFICATIONS:
  THE ROSGEN NATURAL STREAM RESTORATION COURSEWORK TO LEVEL IV (RIVER RESTORATION AND NATURAL CHANNEL DESIGN)
  NORTH CAROLINA STATE UNIVERSITY STREAM RESTORATION PROGRAM TRAINING COURSEWORK EQUIVALENT
  HAVE COMPLETED THE DESIGN AND/OR CONSTRUCTION OF 2 MILES OF STREAM CHANNEL WITH AT LEAST 25% HAVING OCCURRED IN TENNESSEE. MUST SUBMIT PROJECT NAMES, APPLICABLE PERMIT NUMBERS, LENGTH OF PROJECT, AND SHORT DESCRIPTION OF INVOVLMENT. THESE PROJECTS MAY OVERLAP WITH PROJECT REQUIREMENTS BELOW IN (3).
THE NATURAL STREAM CHANNEL CONSTRUCTION/DESIGN EXPERT CAN BE THE SUPERINTENDENT, FOREMAN, A CONSULTANT OR A SUB-
CONTRACTOR THAT SPECIALIZES IN NATURAL STREAM CHANNEL DESIGN AND CONSTRUCTION. PROVIDE DOCUMENTATION OF
REQUIRED TRAINING TO THE TDOT DISTRICT SUPERVISOR AT THE PRE-CONSTRUCTION MEETING.
THE NATURAL STREAM CHANNEL CONSTRUCTION/DESIGN EXPERT SHALL HAVE COMPLETED CONSTRUCTION OF AT LEAST THREE STREAM RESTORATION PROJECTS FOR MITIGATION BANKS, IN LIEU FEE PROGRAMS, OR STANDALONE MITIGATION SITES. THESE THREE PROJECTS SHALL BE BASED ON NATURAL STREAM CHANNEL DESIGN PRINCIPLES INCLUDING, BUT NOT LIMITED TO: IN-STREAM STRUCTURES (STEP POOLS, LOG VANES, ROCK RIFFLES, AND WOOD TOE PROTECTION), STREAM MEANDER CONSTRUCTION, AND STREAMBANK RESTORATION (BANK SHAPING, STABILIZATION, AND BIOENGINEERING), AND VEGETATION INSTALLATION (I.E. NATIVE SEED MIX, BARE ROOT SEEDLINGS, LIVE STAKES, CONTAINER TREES, AND BALLED AND BURLAP TREES). PROVIDE DOCUMENTATION OF THE PROJECTS FOR REVIEW TO THE TDOT DISTRICT SUPERVISOR AT THE PRE-CONSTRUCTION MEETING.
A REGISTERED TENNESSEE PROFESSIONAL ENGINEER WITH KNOWLEDGE OF THE MITIGATION SITE SHALL PREPARE AS-BUILT PLANS OF THE CONSTRUCTED NATURAL STREAM CHANNEL IMMEDIATELY FOLLOWING COMPLETION. A COPY OF THE ORIGINAL NATURAL STREAM CHANNEL PLANS, RED-LINED TO SHOW VARIANCES FROM THE ORIGINAL DESIGN, IS ACCEPTABLE TO MEET THIS REQUIREMENT. A SURVEY QUALITY AS-BUILT PLANS MAY BE REQUIRED IF PERMIT COMPLIANCE ISSUES ARE IDENTIFIED DUE TO DISCREPANCIES IN THE CONSTRUCTED NATURAL STREAM CHANNEL PLANS AND THE PERMITTED NATURAL STREAM CHANNEL PLANS. SUBMIT THE AS-BUILT PLANS TO THE TDOT ENVIRONMENTAL DIVISION MITIGATION OFFICE AT TDOT.ENV.MITIGATION@TN.GOV AND TO THE TDOT DISTRICT SUPERVISOR.

## Slide 9: Borrow Excavation
Item 203-03.51 - Borrow Excavation (Unclassified)
  136,200 cy
  Footnote 10
    Borrow Excavation from adjacent project waste site 101651.01 is available to the contractor and shall be used at the direction of the Engineer.
Additional details, cross-sections, and EPSC sheets will be added to the plans as a letting revision early next week.

## Slide 10: Traffic Control Plan
9 Total Phases including sub-phases
  Phase 1
  Phase 1B
  Phase 1C
  Phase 1D
  Phase 2
  Phase 3A
  Phase 3B
  Phase 3C
  Phase 4

## Slide 11: Airport Coordination
  Obstruction Evaluation/Airport Airspace Analysis (OE/AAA)
    FAA Form 7460-1
    All cranes to be used during the project
    FAA Requests 45-day notice
    We recommend 90 days prior to needing the crane
  Website
      https://oeaaa.faa.gov/

## Slide 12: Airport Coordination

## Slide 13: Airport Coordination

## Slide 14: Utilities
Move In State
AT&T
ATMOS Gas
Charter
City of Alcoa Electric
City of Alcoa Water
City of Alcoa Sewer
City of Maryville Electric
Move Prior (Completed)
Enbridge Gas
Schedule of Calendar Days
AT&T – 678 Days
  AT&T to self-perform certain work
ATMOS
  Estimated 110 Days to stockpile
Charter
  15 Days to complete
COA Electric
  Estimated 14-16 weeks on steel poles
COA Water
  Estimated 300 Days to stockpile
COA Sewer
  Estimated 300 Days to stockpile
COM Electric
  Estimated 210 Days to stockpile, 7 months lead on underground cabinets

## Slide 15: Utility Considerations
Materials and Lead Times
34 Metal poles – 35’ to 75’
13,000’ DIP for water and sewer – 6” to 12”
4,580’ various sized steel casing – 16” to 30”
Underground electric cabinets
Additional Utility Information
Overall sewer depths and casing within stream mitigation area
Each utility will have 2 sets of quantities due to the utility funding source. The break line for the item categories is Sta. 241+50. Each utility will have 2 categories, it is critical that the items are billed to the correct category to ensure utility costs are tracked accurately. This does not apply to Charter and COM electric.

## Slide 16: Bridges (6 Total)
Bridge No. 1 – Wright Road over S.R. 115
  2-Span, 63” Prestressed Concrete Bulb-Tee Girders, 246’-6” Long, Multi-Column Piers, Large Cut
Bridge No. 2 – Regal Drive over Russell Branch and S.R. 115
  4-Span, 72” Prestressed Concrete Bulb-Tee Girders, 445’ Long, Hammerhead Piers
Bridge No. 3 – Ramp A2 over S.R. 162 and S.R. 115
  7-Span, Curved Steel Welded Plate Girders, 1150’ Long, Hammerhead Piers, Drilled Shaft Foundations
Bridge No. 4 – Ramp D2 over S.R. 115, Ramp A2, and S.R. 162
  11-Span, Curved, 72” Prestressed Concrete Bulb-Tee Girders, 1250’ Long, Hammerhead Piers
Bridge No. 5 – Ramp A1 over Cusick Road
  3-Span, Curved, 66” Prestressed Concrete Wide Bulb-Tee Girders, 353’-8¼” Long, Multi-Column Piers
Bridge No. 6 – Ramp B1 over Cusick Road
  3-Span, 63” Prestressed Concrete Bulb-Tee Girders, 211’ Long, Hammerhead Piers

## Slide 17: Geotechnical Challenges
Bridge 3
  Drilled Shaft Foundations
  SP 625
Settlement Monitoring
  Ramps B1 and D2
Soft Soils
  GSR ground improvement
Wall 2 – Under Pellissippi Bridge
  Soil nails designed at steep angles to avoid Bridge Abutment Piles as close as 11 feet away. Need to install 40 degrees from horizontal along with a bottom/toe nail 70 degrees from horizontal to achieve required global stability

## Slide 18: Project Overview
Letting Date: August 18, 2023
The grading, drainage, construction of bridges, retaining walls and paving on U.S. 129 (S.R. 115) from proposed interchange at Tyson Boulevard to existing U.S. 129 (S.R. 115) at South Singleton Station Road.
ADT: 37,250 (New Alignment)
DBE Goal: 9.5%
Completion Date: October 31, 2027
Designer: H. W. Lochner, Inc.
Full CEI oversight

## Slide 19: Special Provision 108B
Any work requiring lane closures including pavement marking operations shall be at night between the hours of 7PM and 6AM (Sunday through Thursday), unless otherwise directed by the TDOT Operations District Engineer and the Regional Traffic Incident Management Coordinator.
No lane closures will be allowed on Saturdays when the University of Tennessee plays football in Knoxville, during Special Events, Holidays or Holiday weekends in accordance with the plans and specifications, or as approved by the TDOT Operations District Engineer and the Regional Traffic Incident Management Coordinator

## Slide 20: Special Provision 108B
Liquidated damages for ITS related outages

## Slide 21: Special Provisions
108C – Liquidated damages for CEI administered contracts
109A & B – Payment adjustment for fuel and bituminous materials
109ETAS – E-ticketing for asphalt
202ACM – Removal of Asbestos Containing Material (ACM)
407IC – Intelligent compaction for hot mix asphalt
411B – Rideability for Asphalt
624 – Retaining Walls
625 – Drilled shafts
700SIG – Highway Signs, Luminaires & Traffic Signals
725 – Technical Specifications
730A – Temporary Traffic Control (Signalization)
790 – Utility Specifications

## Slide 22: Questions
Please submit RFIs by email to Jamie.Fitzpatrick@tn.gov.
Please submit with subject line as, “CNX308 Blount RFI”
RFIs will be accepted up until Friday, August 11, at 4:00 p.m. CDT.
Responses will be posted on TDOT Construction website as informational addendums.

## Slide 23: Questions